## Test summary report
Tester | NHGHieu, PTBTin, VMPhat, VMQuan
Date | 17/12/2024
| Test summary report |  | Link to demo video playlist: https://www.youtube.com/playlist?list=PLEJW8FxF3lU3ItcDX8d-2l1_GeNmpG5MU
| Number of functions be tested | 6
| Number of test cases | 62
| Number of passed test cases | 54
| Number of failed test cases | 8
| Number of bugs | 8

## Bug report
Defect ID | Defect Title | Defect Description / How to reproduce | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | No message is displayed when user logs in with incorrect email | 1. Navigate to Log In page 2. Enter Email: "adm123@gmail.com" 3. Enter Password: "admin123" 4. Click "Log In" button Expected: Unauthenticated and a wrong user-email notice will be displayed Actual: Unauthenticated and no notice is shown | UC01 | Low | VMPhat | 2024-05-12 | Closed
B002 | No message is displayed when user logs in with incorrect password (case-sensitive) | 1. Navigate to Log In page 2. Enter Email: "admin@gmail.com" 3. Enter Password: "Admin123" 4. Click "Log In" button Expected: Unauthenticated and a wrong password notice will be displayed Actual: Unauthenticated and no notice is shown | UC01 | Low | VMPhat | 2024-05-12 | Closed
B003 | Users are allowed to enter names containing special characters | 1. Navigate to Sign Up page 2. Enter Name: "vmphat!@#" 3. Enter Email: "vmphat24@gmail.com" 4. Enter Password: "Vmphat@pic2model" 5. Enter Confirm Password: "Vmphat@pic2model" 6. Click "Sign Up" button Expected: Disallows the user to proceed and displays an error message indicating that the username contains invalid characters Actual: User account is created successfully and the user is redirected to the welcome page | UC03 | Low | VMPhat | 2024-09-12 | Open
B004 | File that is not allowed for generating is allowed to upload | 1. Navigate to Generate page 2. Click "Choose File" button uploade file 3. Choose file .pdf to upload 4. Click "Ok" Expected: File is not allowed Actual: File is allowed | UC05 | Low | NHGHieu | 2024-10-12 | Open | File is allowed to upload but blocked in generating step
B005 | File that is not allowed for generating is allowed to upload | 1. Navigate to Generate page 2. Click "Choose File" button uploade file 3. Choose file .docx to upload 4. Click "Ok" Expected: File is not allowed Actual: File is allowed | UC05 | Low | NHGHieu | 2024-10-12 | Open | File is allowed to upload but blocked in generating step
B006 | File that is not allowed for generating is allowed to upload | 1. Navigate to Generate page 2. Click "Choose File" button uploade file 3. Choose file .txt to upload 4. Click "Ok" Expected: File is not allowed Actual: File is allowed | UC05 | Low | NHGHieu | 2024-10-12 | Open | File is allowed to upload but blocked in generating step
B007 | File that is not allowed for generating is allowed to upload | 1. Navigate to Generate page 2. Click "Choose File" button uploade file 3. Choose file .cpp to upload 4. Click "Ok" Expected: File is not allowed Actual: File is allowed | UC05 | Low | NHGHieu | 2024-10-12 | Open | File is allowed to upload but blocked in generating step
B008 | Can not interact with generated 3D model | 1. Navigate to Generate page 2. Click "Browse" button uploade file 3. Choose file .jpg to upload 4. Click "Ok" 5. Click "Generate" 6. Interact with generated model in album Expected: Generated model is interactable Actual: Generated model is not interactable | UC06 | High | NHGHieu | 17/12/2024 | Open | User can view different angles of model through images, video. But, User can not rotate or scale it on their own.
Note on D1: Function ID of the function where the defect is found
Note on E1: High, Medium, or Low
Note on F1: Name of the tester who reports the defect
Note on H1: Open or Closed